# Maple Street Community Garden

A practical plan for a shared neighborhood growing space

DRAFT PLAN  •  SPRING–FALL 2027  •  24 HOUSEHOLDS

# A small plot with a big purpose

The Maple Street Community Garden will turn an underused corner lot into a welcoming place to grow food, share skills, and spend time outdoors. The first season is intentionally modest: twelve raised beds, a communal herb border, accessible paths, and a shaded gathering table.

## What success looks like

•  Twelve productive plots assigned through a transparent neighborhood lottery.

•  At least four free workshops led by local gardeners and cooks.

•  A shared harvest shelf stocked weekly during peak season.

•  A clean, safe site maintained through rotating volunteer teams.

# Season plan

| Phase | Timing | Primary work | Lead |
| --- | --- | --- | --- |
| Prepare | March | Soil testing, permits, bed assembly, water connection | Site team |
| Plant | April–May | Plot orientation, cool-season crops, herb border | Grow team |
| Tend | June–August | Watering rotations, workshops, shared harvest shelf | Members |
| Close | September–October | Final harvest, compost, repairs, season review | Stewards |

# Budget snapshot

| Item | Estimate | Notes |  |
| --- | --- | --- | --- |
| Raised-bed materials | $2,400 | Twelve cedar beds with hardware |  |
| Soil and compost | $1,350 | Initial fill plus midseason amendment |  |
| Water and tools | $1,100 | Hose system, hand tools, locked storage |  |
| Access and seating | $950 | Path surfacing and one shared table |  |

# First decisions

1. Confirm the lot-use agreement and water access.

2. Approve the initial $5,800 materials budget.

3. Recruit six volunteer stewards before construction weekend.

Design principle: make the garden easy to join, easy to maintain, and generous to the wider neighborhood.